## Summary
OJT Training - Summary
| Training Start Date |  |  | Total Days | 77.25
Training End Date
S. No | Course | Course Objectives | Week | Content | Days
1 | GuruBanking | 1. Test process 2. Study Requirement, create QA 3. Create Testcases 4. Review Testcases using checklist 5. Execute Test 6. Log bug, create test report | Week 1 | - Project Kickoff - Submit account - Study Requirement, create QA - Create Integration Testcase following SRS v1 - Review Testcase | 19.25 | Rút ngắn thời gian training phần Guru Banking -7days
|  |  | Week 2 | - How to log bug, create test report - Execute Test v1 - Update Test case following SRS v2
|  |  | Week 3 | - Execute Test v2 - Update Test case following SRS v3 - Execute Test v3 - Update Test case following SRS v4 - Create system Test case
|  |  | Week 4 | - Execute Test v4 - Test Closure Activities
2 | Accessibility testing | 1. Have overview about accessibility testing 2. Familiar with using necessary tools to perform accessibility testing 3. Study, reseach 78 rules in WCAG 4. Log bug based on sample template 5. Get Trusted Tester - Certification Exam for Web on Windows | Week 1 | - Have basic understanding about accessibility testing - Know how to use necessary tools - Study about the first 26 important rules in WCAG (bugs are likely to exist) - Log bug | 18 | Rút ngắn thời gian training phần Accessibility -5days
|  |  | Week 2 | - Study about the next 9 important rules in WCAG (bugs are likely to exist) - Study on how to make attachements (video/screenshots) - Log bug based on sample template
|  |  | Week 3 | - Self-study and research about the remaining WCAG rules - Finish all 5 modules in Section 508 - Log bug based on sample template
|  |  | Week 4 | Finish the last module to get Trusted Tester - Certification Exam for Web on Windows
3 | Automation testing |  | Week 1 | Selenium WebDriver API | 20 | Automation tăng thêm 12 days
|  |  | Week 2 | Automation Testing Framework |  | (Automation advance: 20 days)
|  |  | Week 3 | Automation Testing Framework and Jenkins
|  |  | Week 4 | 1. API Testing 2. API manual Testing with Postman. 3. API automation testing with Postman.
4 | ISTQB | 1. Overview of ISTQB exam 2. Have knowledge about each chapter in ISTQB foundation syllabus 3. Study Dump question to prepare for ISTQB Exam | Week 1 | Introduction ISTQB exam 1. Fundamental of Testing 2. Throughout the Software Development Lifecycle 3. Static Testing 4. Test Techniques | 20
|  |  | Week 2 | 5. Test Management 6. Tool Support for Testing Review after studying
|  |  | Week 3 | Study Dump question to join ISTQB Exam
|  |  | Week 4 | Study Dump question to join ISTQB Exam

## GuruBanking
OJT Training - GuruBanking
|  | Training Start Date | Total Hours |  | 154
|  | Training End Date | Total Days |  | 19.25
Week | Day | Module | Duration (Hours) | Start Date | End Date | Status | Trainer Name | Training Materials
1 | 1 | Project Kickoff Submit an account Give Req v1, Testcase template | 2 | 2022-12-06 | 2022-12-06 | Done | Thuy Vu/Ngoan Khuong | Day 01
|  | Study Requirement, create QA | 6 | 2022-12-06 | 2022-12-06 | Done | Self-Study
| 2 | Daily meeting Answer QAs after studying Requirement Guide Testcase template | 2 | 2022-12-07 | 2022-12-07 | Done | Thuy Vu/Ngoan Khuong | Day 02
|  | Create TC V1 | 6 | 2022-12-07 | 2022-12-07 | Done | Self-Study
| 3 | Daily meeting Review created TCs quickly and give comment Test technique (Equivalence Partitioning & Boundary Testing) | 0.5 | 2022-12-08 | 2022-12-08 | Done | Thuy Vu/Ngoan Khuong | Day 03
|  | Create and Update TCs following comments | 7.5 | 2022-12-08 | 2022-12-08 | Done | Self-Study
| 4 | Daily meeting Review and evaluate progress Review Knowledge: self review, peer review, test lead review Guide how to use Checklist | 1 | 2022-12-09 | 2022-12-09 | Done | Thuy Vu/Ngoan Khuong | Day 04
|  | Peer Review TC | 7 | 2022-12-09 | 2022-12-09 | Done | Self-Study
| 5 | Daily meeting Evaluate Review progress | 0.5 | 2022-12-12 | 2022-12-12 | Done | Thuy Vu/Ngoan Khuong | Day 05
|  | Review TC + Update | 7.5 | 2022-12-12 | 2022-12-12 | Done | Self-Study
2 | 6 | Daily meeting Evaluate Review progress | 0.5 | 2022-12-13 | 2022-12-13 | Done | Thuy Vu/Ngoan Khuong
|  | Review TC + Update | 7.5 | 2022-12-13 | 2022-12-13 | Done | Self-Study
| 7 | Daily meeting Learn how to log bug, create test report Explain testing life cycle | 2 | 2022-12-14 | 2022-12-14 | Done | Thuy Vu/Ngoan Khuong | Day 07
|  | Execute Test http://demo.guru99.com/V1/ | 6 | 2022-12-14 | 2022-12-14 | Done | Self-Study | http://demo.guru99.com/
| 8 | Execute Test V1 | 8 | 2022-12-15 | 2022-12-15 | Done | Self-Study | Day 08
| 9 | Daily meeting: Evaluate Bug that members found How to create MR, Create rule for mail, book meeting room Give Req v4 | 0.5 | 2022-12-16 | 2022-12-16 | Done | Thuy Vu/Ngoan Khuong | Day 09
|  | Create/Update TC following Req v4 | 7.5 | 2022-12-16 | 2022-12-16 | Done | Self-Study
| 10 | Create/Update TC following Req v4 | 8 | 2022-12-19 | 2022-12-19 | Done | Self-Study
3 | 11 | Daily meeting Evuluate TCs Req v4: Missing TC, Missing req,... Explain Test Level: Unit Test, Intergration Test, System Test, UAT Give some example: What is Intergration Test, System Test | 1 | 2022-12-20 | 2022-12-20 | Done | Thuy Vu/Ngoan Khuong
|  | Peer Review TC | 7 | 2022-12-21 | 2022-12-21 | Done | Self-Study
| 12 | Update after Reviewing | 8 | 2022-12-22 | 2022-12-22 | Done | Self-Study
| 13 | Daily meeting Learn how to create system test case | 0.5 | 2022-12-23 | 2022-12-23 | Done | Thuy Vu/Ngoan Khuong
|  | Create System TC | 7.5 | 2022-12-23 | 2022-12-23 | Done | Self-Study
| 14 | Daily meeting: Quick Review System TCs Req v4 | 0.5 | 2022-12-24 | 2022-12-24 | Done | Thuy Vu/Ngoan Khuong
|  | Update + Create System TC | 7.5 | 2022-12-24 | 2022-12-24 | Done | Self-Study
| 15 | Peer Review system TC | 8 | 2022-12-26 | 2022-12-26 | Done | Self-Study
4 | 16 | Daily meeting Evaluate Review progress Testing principles | 0.5 | 2022-12-27 | 2022-12-27 | Done | Thuy Vu/Ngoan Khuong
|  | Peer Review system TC | 7.5 | 2022-12-27 | 2022-12-27 | Done | Self-Study
| 17 | Daily meeting Evaluate System TC detail | 0.5 | 2022-12-28 | 2022-12-28 | Done | Thuy Vu/Ngoan Khuong | Day 17
|  | Execute Test http://demo.guru99.com/V4/ | 7.5 | 2022-12-28 | 2022-12-28 | Done | Self-Study
| 18 | Daily meeting | 0.5 | 2022-12-29 | 2022-12-29 | Done | Thuy Vu/Ngoan Khuong
|  | Execute Test http://demo.guru99.com/V4/ | 7.5 | 2022-12-29 | 2022-12-29 | Done | Self-Study
| 19 | Daily meeting How to test GUI | 0.5 | 2022-12-30 | 2022-12-30 | Done | Thuy Vu/Ngoan Khuong
|  | Execute GUI test base on Mockup file | 7.5 | 2022-12-30 | 2022-12-30 | Done | Self-Study | Chrome Zoom 50%-200%
| 20 | TestClosure Activities Evaluation after training | 2 | 2023-01-03 | 2023-01-03 |  | Thuy Vu/Ngoan Khuong

## Accessibility testing
OJT Training - Accessibility testing
|  | Training Start Date | Total Hours |  | 135
|  | Training End Date | Total Days |  | 18 | Cân nhắc giảm duration
Week | Day | Module | Duration (Hours) | Start Date | End Date | Trainer Name | Training Materials
1 | 1 | 1. Briefly introduce about Accessibility Testing: 1a. What is is? 1b. Why accessibility testing? 1c. Which Disabilities to Support? 1d. How to do accessibility testing? 1e. Accessibility Testing tools 2. Install neccessary tools: NVDA Screen Reader, Colour Constrast Analyzer, Google Chrome 3. How to register an account for Section 508 | 2 | 2023-04-01 | 2023-04-01 | Nam Bui/Huy Vu/ Thuy Vu | Day 01
| 2 | 1. NVDA Settings 2. Present about rules: 1.1.1 Non-text content 1.2.1. Audio-only and Video-only 1.2.2. Captions (Prerecorded) 1.2.3. Audio Description or Media 1.2.4. Captions (Live) 1.2.5. Audio Description (Prerecorded) | 1 | 2023-05-01 | 2023-05-01 | Huy Vu | Day 02
|  | 3. Homework: Revise 6 above rules Finish the first 3 modules in section 508 5. Optional: watch training videos of the previous batch https://hclo365-my.sharepoint.com/personal/kusum_k_hcl_com/_layouts/15/onedrive.aspx?id=%2Fpersonal%2Fkusum%5Fk%5Fhcl%5Fcom%2FDocuments%2FBatch%2012%20Recorded%20Session&ct=1667888905050&or=Teams%2DHL&ga=1 | 7 | 2023-05-01 | 2023-05-01 | Self-Study
| 3 | 2. Present about rules: 2.1.1 Keyboard 2.4.3. Focus order (logical) 2.4.7. Focus visbile 2.1.4. Character Key Shortcut 2.1.2. No keyboard trap | 1 | 2023-06-01 | 2023-06-01 | Nam Bui | Day 03
|  | 3. Homework: assign webpage test -> log bug (based on studied rules) 4. Finish the first 3 modules in section 508 5. Optional: watch training videos of the previous batch https://hclo365-my.sharepoint.com/personal/kusum_k_hcl_com/_layouts/15/onedrive.aspx?id=%2Fpersonal%2Fkusum%5Fk%5Fhcl%5Fcom%2FDocuments%2FBatch%2012%20Recorded%20Session&ct=1667888905050&or=Teams%2DHL&ga=1 | 6.5 | 2023-06-01 | 2023-06-01 | Self-Study
| 4 | 1. Check homework | 0.5 | 2023-09-01 | 2023-09-01 | Huy Vu | Day 04
|  | 2. Present about rules: 3.2.1. On focus 3.2.2. On input 1.4.1. Use of color 1.4.5. Images of text 2.4.1. Bypass blocks | 1 | 2023-09-01 | 2023-09-01 | Huy Vu
|  | 3. Homework: assign webpage test -> log bug (based on studied rules) 4. Finish the first 3 modules in section 508 5. Optional: watch training videos of the previous batch https://hclo365-my.sharepoint.com/personal/kusum_k_hcl_com/_layouts/15/onedrive.aspx?id=%2Fpersonal%2Fkusum%5Fk%5Fhcl%5Fcom%2FDocuments%2FBatch%2012%20Recorded%20Session&ct=1667888905050&or=Teams%2DHL&ga=1 | 6.5 | 2023-09-01 | 2023-09-01 | Self-Study
| 5 | 1. Present about rules: 1.4.3. Constrast minimum 1.4.11. Non-text constrast 1.4.4. Resize 1.4.10. Reflow 1.4.12. Text spacing | 1 | 2023-10-01 | 2023-10-01 | Nam Bui | Day 05
|  | 2. Finish the first 3 modules in section 508 3. Optional: watch training videos of the previous batch https://hclo365-my.sharepoint.com/personal/kusum_k_hcl_com/_layouts/15/onedrive.aspx?id=%2Fpersonal%2Fkusum%5Fk%5Fhcl%5Fcom%2FDocuments%2FBatch%2012%20Recorded%20Session&ct=1667888905050&or=Teams%2DHL&ga=1 | 6.5 | 2023-10-01 | 2023-10-01 | Self-Study
2 | 6 | 1. Check homework | 0.5 | 2023-11-01 | 2023-11-01 | Huy Vu | Day 06
|  | 2. Present about rules: 1.3.3. Sensory Characteristics 1.3.5. Identify input purpose 1.4.13. Content on hover 3.3.2. Label or instruction 2.4.6. Headings and labels | 1 | 2023-11-01 | 2023-11-01 | Huy Vu
|  | 2. Finish the first 3 modules in section 508 3. Optional: watch training videos of the previous batch https://hclo365-my.sharepoint.com/personal/kusum_k_hcl_com/_layouts/15/onedrive.aspx?id=%2Fpersonal%2Fkusum%5Fk%5Fhcl%5Fcom%2FDocuments%2FBatch%2012%20Recorded%20Session&ct=1667888905050&or=Teams%2DHL&ga=1 | 6.5 | 2023-11-01 | 2023-11-01 | Self-Study
| 7 | 1. Present about rules: 3.3.1. Error identification 3.3.3. Error suggestion 3.3.4. Error prevention 3.2.4. Consistent identification 2.4.4. Link purpose | 1 | 2023-12-01 | 2023-12-02 | Nam Bui | Day 07
|  | 2. Finish the first 3 modules in section 508 3. Optional: watch training videos of the previous batch https://hclo365-my.sharepoint.com/personal/kusum_k_hcl_com/_layouts/15/onedrive.aspx?id=%2Fpersonal%2Fkusum%5Fk%5Fhcl%5Fcom%2FDocuments%2FBatch%2012%20Recorded%20Session&ct=1667888905050&or=Teams%2DHL&ga=1 | 6.5 | 2023-12-01 | 2023-12-02 | Self-Study
| 8 | 1. Present about rules: 1.3.1. Info and relationship 4.1.2. Name, role, value/state 2.5.3. Label in name 4.1.3. Status messages | 1 | 13/1/2023 | 13/1/2023 | Huy Vu | Day 08
|  | 2. Homework: assign webpage test -> log bug 3. Finish the first 3 modules in section 508 4. Optional: watch training videos of the previous batch https://hclo365-my.sharepoint.com/personal/kusum_k_hcl_com/_layouts/15/onedrive.aspx?id=%2Fpersonal%2Fkusum%5Fk%5Fhcl%5Fcom%2FDocuments%2FBatch%2012%20Recorded%20Session&ct=1667888905050&or=Teams%2DHL&ga=1 | 6.5 | 13/1/2023 | 13/1/2023 | Self-Study
| 9 | 1. Check homework | 0.5 | 16/1/2023 | 16/1/2023 | Nam Bui | Day 09
|  | 2. Instruction on how to create attachements: screenshots/videos | 1 | 16/1/2023 | 16/1/2023 | Nam Bui
|  | 3. Homework: assign webpage test -> log bug -> make attachements 4. Research and self-study about the remaining rules 5. Finish module 4 & 5 in Section 508 | 6.5 | 16/1/2023 | 16/1/2023 | Self-Study
| 10 | 1. Check homework | 0.5 | 17/1/2023 | 17/1/2023 | Huy Vu | Day 10
|  | 2. How to write User experience, Step reproduce, Expected Result, Actual result trong file log bug | 1 | 17/1/2023 | 17/1/2023 | Huy Vu
|  | 3. Homework: assign webpage test -> log bug based on sample template 4. Research and self-study about the remaining rules 5. Finish module 4 & 5 in Section 508 | 6.5 | 17/1/2023 | 17/1/2023 | Self-Study
3 | 11 | 1. Check homework | 1 | 30/1/2023 | 30/1/2023 | Nam Bui | Day 11
|  | 2. Research and self-study about the remaining rules 3. Finish module 4 & 5 in Section 508 | 7 | 30/1/2023 | 30/1/2023 | Self-Study
| 12 | 1. Finish module 4 & 5 in Section 508 2. Research and self-study about the remaining rules | 8 | 31/1/2023 | 31/1/2023 | Self-Study | Day 12
| 13 | 1. Homework: assgin webpage to test -> log bug based on sample template 2. Finish module 4 & 5 in Section 508 3. Research and self-study about the remaining rules | 8 | 2023-01-02 | 2023-01-02 | Self-Study | Day 13
| 14 | 1. Finish module 4 & 5 in Section 508 2. Self-revision about all rules in WCAG | 8 | 2023-02-02 | 2023-02-02 | Self-Study | Day 14
| 15 | 1. Check homework | 1 | 2023-03-02 | 2023-03-02 | Huy Vu
|  | 2. Homework: assign webpage test -> log bug based on sample template 3. Finish the last module to get certificate Trusted Tester - Certification Exam for Web on Windows | 7 | 2023-03-02 | 2023-03-02 | Self-Study | Day 15
4 | 16 | 2. Finish the last module to get certificate Trusted Tester - Certification Exam for Web on Windows | 7 | 2023-06-02 | 2023-06-02 | Self-Study | Day 16
| 17 | Finish the last module to get certificate Trusted Tester - Certification Exam for Web on Windows | 8 | 2023-07-02 | 2023-07-02 | Self-Study
| 18 | Finish the last module to get certificate Trusted Tester - Certification Exam for Web on Windows | 8 | 2023-08-02 | 2023-08-02 | Self-Study

## AUTO
OJT Training - Selenium Java
|  | Training Start Date | Total Hours |  | 162
|  | Training End Date | Total Days |  | 20.25
Week | Day | Module | Duration (Hours) | Start Date | End Date | Trainer Name | Training Materials
1 | 1--5 | Introduction |  |  |  | Minh Lee
|  | Introducting KiotViet's system to write test cases and the course | 32 | 2023-10-02 | 16/2/2023 | Minh Lee |  | Giảm thời gian viết TCs còn 2 ngày
|  | Reviewing test cases | 8 | 17/2/2023 | 17/2/2023 | Minh Lee
2 | 6 | XPath and Css Selector
|  | Locator | 2 | 20/2/2023 | 20/2/2023 | Minh Lee | VS Code and https://opensource-demo.orangehrmlive.com/web/index.php/auth/login
Tips and tricks
Find locator plugin/ extensions
|  | Practicing | 4 |  |  | Self-Study
Selenium WebDriver API
| 7 | Review | 1
|  | Handle dropdown list (Angular/ JQuery, React..) | 2 | Done | Done | Minh Lee | VS Code and https://opensource-demo.orangehrmlive.com/web/index.php/auth/login
|  | Practicing | 5 |  |  | Self-Study
| 8 | Review | 1
|  | User interaction ( keyboard and mouse ) | 3 | Done | Done | Minh Lee | VS Code and https://opensource-demo.orangehrmlive.com/web/index.php/auth/login
|  | Practicing | 4 |  |  | Self-Study
| 9 | Review | 1
|  | Handle windows and tabs | 2 | Done | Done | Minh Lee | VS Code and https://opensource-demo.orangehrmlive.com/web/index.php/auth/login
|  | Practicing | 5 |  |  | Self-Study
| 10 | Review | 1
|  | Handle popup, alert and frame | 2 | Done | Done | Minh Lee | VS Code and https://opensource-demo.orangehrmlive.com/web/index.php/auth/login
|  | Practicing | 5 |  |  | Self-Study
3 | 11 | Review | 1
|  | Javascript Executor | 2 | Done | Done | Minh Lee
|  | Practicing | 5 |  |  | Self-Study
| 12 | Review | 1
|  | Wait ( implicit, explicit, fluent) | 2 | 28/2/2023 | 28/2/2023 | Minh Lee | VS Code and https://opensource-demo.orangehrmlive.com/web/index.php/auth/login
|  | Practicing | 5 |  |  | Self-Study
| 13 | Automation Testing Framework
|  | Review | 1 |  | Practicing | 3
|  | Create AT Framework structure | 2 | 21/2/2023 | 21/2/2023 | Minh Lee | VS Code and https://opensource-demo.orangehrmlive.com/web/index.php/auth/login
|  | Apply Page Object Model | 2 | 21/2/2023 | 21/2/2023
|  | Practicing | 3 |  |  | Self-Study
| 14 | Review | 1
|  | Selenium Page Factory | 2 | 28/2/2023 | 28/2/2023 | Minh Lee | VS Code and https://opensource-demo.orangehrmlive.com/web/index.php/auth/login
|  | Practicing | 5 |  |  | Self-Study
| 15 | Review | 1
|  | Dynamic locator and Rest parameter | 2 | 23/2/2023 | 23/2/2023
|  | Practicing | 5 |  |  | Self-Study
4 | 16 | Review | 1
|  | Assert and Verify | 2 | 2023-01-03 | 2023-01-03 | Minh Lee | VS Code and https://opensource-demo.orangehrmlive.com/web/index.php/auth/login
|  | Practicing | 5 |  |  | Self-Study
| 17 | Review | 1
|  | Report ( Extend report ) | 2 | Pending |  | Minh Lee | VS Code and https://opensource-demo.orangehrmlive.com/web/index.php/auth/login
|  | Handel headless browser ( chrome, firefox) | 2 | 2023-03-03 | 2023-03-03
|  | Practicing | 3 |  |  | Self-Study
| 18 | Jenkins |  | Pending
|  | Review | 1
|  | Install jenkins | 4 |  |  | Minh Lee | VS Code and https://opensource-demo.orangehrmlive.com/web/index.php/auth/login
|  | Intergate Github vs jenkins | 2
Build jobs
|  | Practicing | 1 |  |  | Self-Study
19 |  | Log4j | 1
20 |  | Allua | 1
21 |  | cucumber | 7
22 |  | Selenium Grid | 3
23 |  | Jenkins | 4
24 |  | Maven | 4
25 |  | robot fw | options
chiều nay |  | 2 bài toán thiếu nhi + 1 bài automation
Phương, Thúy, Ánh, Dũng, Đạt, Mẫn

## AUTO-API
OJT Training - AUTO-API
|  | Training Start Date | Total Hours |  | 56
|  | Training End Date | Total Days |  | 7
Week | Day | Module | Duration (Hours) | Start Date | End Date | Trainer Name | Training Materials
1 | 1 | API Overview | 0.5 | 2023-03-06 | 2023-03-06 | Hoang Vu
|  | Type of APIs (Soap vs Rest) | 0.5 |  |  | Hoang Vu |  | Tăng thời gian review
|  | Type of Methods (PUT, POST, GET, DELETE). | 1 |  |  | Hoang Vu |  | Tăng bài tập
|  | Header & Response | 1 |  |  | Hoang Vu
|  | Research above topics | 5 |  |  | Self-Study
| 2 | Response Code | 0.5 |  |  | Hoang Vu
|  | How to call API manually in Postman | 1 |  |  | Hoang Vu | Postman tool
|  | Practice to call & analyze the api with Postman | 6.5 |  |  | Self-Study
| 3 | How to write automated API tests in Postman | 2 |  |  | Hoang Vu
|  | Practice to write automated API tests in Postman | 6 |  |  | Self-Study
| 4 | How to run automated API tests in Pipeline with Newman (Part 1) | 2 |  |  | Hoang Vu | Newman tool
|  | Practice to run automated API tests with Newman | 6 |  |  | Self-Study | Newman tool
| 5 | How to run automated API tests in Pipeline with Newman (Part 2) | 2 |  |  | Hoang Vu | Newman tool
|  | Practice to run automated API tests with Newman | 6 |  |  | Self-Study | Newman tool
2 | 6 | Practice automated API tests. | 8 |  |  | Self-Study
| 7 | Demo and evaluation | 8 |  |  | Hoang Vu
Có 6 slides ~ 6 days Mỗi mục 2-3 bài tập Plan: 9-Dec

## ISTQB
OJT Training - ISTQB
|  | Training Start Date | Total Hours |  | 160
|  | Training End Date | Total Days |  | 20
Week | Day | Module | Duration (Hours) | Start Date | End Date | Trainer Name | Training Materials
1 | 1 | Overview of ISTQB exam 1. Fundamental of Testing | 2 |  |  | Thuy Vu/Ngoan Khuong | ISTQB
|  | Self-Study + make Presentation | 6 |  |  | Self-Study
| 2 | 2. Throughout the Software Development Lifecycle | 2 |  |  | Thuy Vu/Ngoan Khuong
|  | Self-Study + make Presentation | 6 |  |  | Self-Study
| 3 | 3. Static Testing | 2 |  |  | Thuy Vu/Ngoan Khuong
|  | Self-Study + make Presentation | 6 |  |  | Self-Study
| 4 | 4. Test Techniques | 2 |  |  | Thuy Vu/Ngoan Khuong
|  | Self-Study + make Presentation | 6 |  |  | Self-Study
| 5 | 5. Test Management | 2 |  |  | Thuy Vu/Ngoan Khuong
|  | Self-Study + make Presentation | 6 |  |  | Self-Study
2 | 6 | 6. Tool Support for Testing | 2 |  |  | Thuy Vu/Ngoan Khuong
|  | Self-Study + make Presentation | 6 |  |  | Self-Study
| 7 | Review after studying | 8 |  |  | Thuy Vu/Ngoan Khuong
| 8 | Review after studying | 8 |  |  | Thuy Vu/Ngoan Khuong
| 9 | Study Dump question to join ISTQB Exam | 8 |  |  | Self-Study
| 10 | Study Dump question to join ISTQB Exam | 8 |  |  | Self-Study
3 | 11 | Study Dump question to join ISTQB Exam | 8 |  |  | Self-Study
| 12 | Study Dump question to join ISTQB Exam | 8 |  |  | Self-Study
| 13 | Study Dump question to join ISTQB Exam | 8 |  |  | Self-Study
| 14 | Study Dump question to join ISTQB Exam | 8 |  |  | Self-Study
| 15 | Study Dump question to join ISTQB Exam | 8 |  |  | Self-Study
4 | 16 | Study Dump question to join ISTQB Exam | 8 |  |  | Self-Study
| 17 | Study Dump question to join ISTQB Exam | 8 |  |  | Self-Study
| 18 | Study Dump question to join ISTQB Exam | 8 |  |  | Self-Study
| 19 | Study Dump question to join ISTQB Exam | 8 |  |  | Self-Study
| 20 | Study Dump question to join ISTQB Exam | 8 |  |  | Self-Study

## Test case writing excercises
Consider đưa bài tập phần Automotive
Đưa all exercise lên shared folders
19-May: hoàn thành update